## Sheet1
The Daily Bean (Coffee-Commerce)
Members:
Bien, Moriel Edgar
Olamit, Jian Lev
So, Alec Giuseppe
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | Sept | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
1. Setup
1.1. Finish Figma UI/UX | Olamit, Jian Lev | 2024-09-28 | 2024-10-01 | Done
1.2. Tweak ERD | Olamit, Jian Lev | 2024-09-29 | 2024-10-01 | Done
1. Login
1.1. Create the Login page | Bien, Moriel Edgar | 2024-09-28 | 2024-10-01 | Done
1.2. Login & Signup on Login page | Bien, Moriel Edgar | 2024-09-28 | 2024-10-02 | Done
2. Home: part 1
2.1. Create the Home page | So, Alec Giuseppe | 2024-09-24 | 2024-09-24 | Done
2.2. Add redirect to Login page if not logged in | So, Alec Giuseppe | 2024-09-28 | 2024-09-30 | Done
2.3. Add account session | So, Alec Giuseppe | 2024-09-29 | 2024-10-01 | Done
3. Account: part 1
3.1. Create the Account page | Olamit, Jian Lev | 2024-09-28 | 2024-09-30 | Done
3.2. Add edit account on Account Information section | Olamit, Jian Lev | 2024-09-28 | 2024-10-03 | Done
3.3. Add edit password on Change Password section | Olamit, Jian Lev | 2024-09-28 | 2024-10-03 | Done
4. Products: part 1
4.1. Create the Product | Bien, Moriel Edgar | 2024-10-11 | 2024-10-14 | Done
4.2. Create the Create Product page (for admins only) | So, Alec Giuseppe | 2024-10-12 | 2024-10-14 | Done
4.3. Add create product on Create Product page (for admins only) | So, Alec Giuseppe | 2024-10-14 | 2024-10-16 | Done
4.4. Add read product on Product page | Bien, Moriel Edgar | 2024-10-13 | 2024-10-16 | Done
4.5. Create the View Product page | Olamit, Jian Lev | 2024-10-11 | 2024-10-14 | Done
4.6. Add read product on View Product page | Olamit, Jian Lev | 2024-10-13 | 2024-10-16 | Done
5. Rework Templates
5.1. _base.html | Olamit, Jian Lev | 2024-10-18 | 2024-10-20 | Done
5.2. add_product.html | Olamit, Jian Lev | 2024-10-18 | 2024-10-20 | Done
5.3. modify_product.html | Olamit, Jian Lev | 2024-10-18 | 2024-10-20 | Done
5.4. product_page.html | Olamit, Jian Lev | 2024-10-18 | 2024-10-20 | Done
5.5. accounts.html | So, Alec Giuseppe | 2024-10-18 | 2024-10-20 | Done
5.6. cart.html | So, Alec Giuseppe | 2024-10-18 | 2024-10-20 | Done
5.7. home.html | So, Alec Giuseppe | 2024-10-18 | 2024-10-20 | Done
5.8. login.html | So, Alec Giuseppe | 2024-10-18 | 2024-10-20 | Done
5.9. product_detail.html | Bien, Moriel Edgar | 2024-10-18 | 2024-10-20 | Done
5.10. products.html | Bien, Moriel Edgar | 2024-10-18 | 2024-10-20 | Done
5.11. signup.html | Bien, Moriel Edgar | 2024-10-18 | 2024-10-20 | Done
6. Order
6.1. Implement Subscriptions tab | Bien, Moriel Edgar | 2024-10-18 | 2024-10-20 | Done
6.2. Clean up code | Olamit, Jian Lev | 2024-10-18 | 2024-10-30 | Done
6.3. Create the Cart page | So, Alec Giuseppe | 2024-10-18 | 2024-10-30 | Done
6.4. Create the Payments page | Bien, Moriel Edgar | 2024-10-18 | 2024-10-30 | Done
6.5. Add read order on Cart page | So, Alec Giuseppe | 2024-10-22 | 2024-11-02 | Done
6.6. Add view orders on Payments page | Bien, Moriel Edgar | 2024-10-22 | 2024-11-02 | Done
7. Account: part 2
7.1. Add addresses on Address section | Olamit, Jian Lev | 2024-10-22 | 2024-11-02 | Done
7.2. Add view order on Payment History | Olamit, Jian Lev | 2024-10-22 | 2024-11-02 | Done
8. Products: part 2
8.1. Implement card payment functionality | Bien, Moriel Edgar | 2024-11-04 | 2024-11-17 | Done
8.1. Add view subscription on Current Subscriptions | Olamit, Jian Lev | 2024-11-04 | 2024-11-17 | Done
8.2. Add favorites dropdown on header | So, Alec Giuseppe | 2024-11-04 | 2024-11-17 | Done
8.3. Add products on favorites dropdown | So, Alec Giuseppe | 2024-11-04 | 2024-11-17 | Done
8.4. Add comments on View Product page | Olamit, Jian Lev | 2024-11-04 | 2024-11-17 | Done
8.5. Add search functionality on Product/Subscription page | Bien, Moriel Edgar | 2024-11-04 | 2024-11-17 | Done
9. Home: part 2
9.1. Add featured products | So, Alec Giuseppe | 2024-11-18 | 2024-11-29 | Done
10. Fixes & Finalizing
10.1. Clean up code | So, Alec Giuseppe | 2024-11-18 | 2024-12-02 | Done
10.2. Add a phone number on User entity | Bien, Moriel Edgar | 2024-11-23 | 2024-12-02 | Done
10.3. Add delete user | Bien, Moriel Edgar | 2024-11-23 | 2024-12-02 | Done
10.4. Add an alert for out of stock products on subscribed users | Olamit, Jian Lev | 2024-11-23 | 2024-12-02 | Done
11. Bug Fixing
11.1. Run tests to figure out bugs | Bien, Moriel Edgar & So, Alec Giuseppe | 2024-11-28 | 2024-12-03 | Done
11.2. Fix those bugs | Olamit, Jian Lev | 2024-12-02 | 2024-12-04 | Done